Operations & Training Risk Management Plan
Author: Project Manager / Status: Draft	Created: Mar 1 / Updated: Mar 31

Objective
The objective of this document is to mitigate upcoming budget risk and people training risk which may slow down the project.

Executive Summary
Project Pals Project is designed to fast deliver its product to the customer and training to employees to achieve that with new software and instruments.
After researching about the project, it is assumed that the project budget may go over and the training schedule may fall.
This document is to mitigate the above two risks.

RISK TYPE ONE: Going over the project budget

Scenario	Risk to project (L/M/H)	Mitigation Plan
Each delivery truck costs $16,000 more than initially quoted.	H	Avoid ( Plan to arrange 2 new drivers with set budget)
A product vendor charges a higher rate than expected.	M	Minimize( the rate with both parties agreable price by effective negotiation)
A product vendor loses a product shipment.	L	Minimize ( By keep contacting and controlling on daily basis)

RISK TYPE TWO: Falling behind the training schedule

Scenario	Risk to project (L/M/H)	Mitigation Plan
Your Training Manager gets sick and misses a week of training.	L	Transfer ( Trainee can practice or do another job which was taught earlier this week.)
You cannot hire enough employees in time to train them before launch.	M	Minimize (by including consultancies or by taking different job related app to hire people)
More than 50% of employees quit after a difficult training process, leaving the company short-staffed.	H	Minimize (Make Training program in such way that it could be not difficult and attention to be given an individual)

Appendix:

Probability chart:

Probability
	Qualitative	Quantitative (if measurable)
Low	Very low chance of risk occurring.	Less than <10% chance of risk occurring.

Medium	Medium chance of risk occurring.	10%-49% chance of risk occurring.
High	High chance of risk occurring.	50%-100% chance of risk occurring.

Impact chart:

Types of Impact	Low	Medium	High
Financial	Low financial impact, / costing the company $0-$14,000	Medium financial impact, / costing the company $15,000-$29,000	High financial impact, / costing the company $30,000 or more
Operational	Low impact to project operations, causing delays of a few days to a few weeks	Medium impact to project operations, / with potential to delay project by a month or more	High impact to project operations, / with potential to cause project failure
People	Low impact to employee attrition, with 5%+ of employees quitting	Medium impact to employee attrition, with 25%+ of employees quitting	High impact to employee attrition, with 50%+ employees quitting

Probability and Impact Matrix:

Inherent Risk
		Impact
		Low	Medium	High
Probability	High	Medium	High	High
	Medium	Low	Medium	High
	Low	Low	Low	Medium